## Project Planner
SYD Airbnd Data Analysis and Visualisation Tool
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1. Initial
1.1 Meeting with group members | 1 | 1 | 1 | 1 | 100%
1.2 Project briefing | 1 | 1 | 1 | 1 | 100%
1.3 Install required application | 1 | 1 | 1 | 2 | 100%
1.4 Task & responsibilities assignment | 1 | 1 | 1 | 1 | 100%
2. Planning
2.1 Project plan | 2 | 3 | 2 | 4 | 100%
2.1.1 Background | 2 | 1 | 1 | 1 | 100%
2.1.2 Scope | 2 | 1 | 2 | 1 | 100%
2.1.3 Document contents | 2 | 1 | 2 | 1 | 100%
2.1.4 Work breakdown structure | 3 | 1 | 3 | 2 | 100%
2.1.5 Activity definition & estimation | 3 | 1 | 3 | 2 | 100%
2.1.6 Gantt chart | 4 | 1 | 4 | 1 | 100%
2.2 Software design document | 5 | 8 | 5 | 7 | 100%
2.2.1 System vision | 5 | 1 | 5 | 1 | 100%
2.2.1.1 Problem background | 5 | 1 | 5 | 1 | 100%
2.2.1.2 System overview | 5 | 1 | 5 | 1 | 100%
2.2.1.3 Potential benefits | 5 | 1 | 5 | 1 | 100%
2.2.2 Requirements | 6 | 3 | 6 | 2 | 100%
2.2.2.1 User requirements | 6 | 1 | 6 | 1 | 100%
2.2.2.2 Software requirements | 7 | 1 | 7 | 1 | 100%
2.2.2.3 Use cases | 8 | 1 | 7 | 1 | 100%
2.2.3 System components & software design | 9 | 2 | 9 | 3 | 100%
2.2.3.1 Software design | 9 | 1 | 9 | 1 | 100%
2.2.3.2 System components | 10 | 1 | 10 | 2 | 100%
2.2.4 User interface design | 11 | 2 | 11 | 2 | 100%
2.2.4.1 Structural design | 12 | 1 | 12 | 1 | 100%
2.2.4.2 Visual design | 13 | 1 | 13 | 1 | 100%
3. Implementation
3.1 Build up a back-end database | 14 | 1 |  |  | 0%
3.2 Create user interface | 15 | 2 |  |  | 0%
3.3 Create algorithms to sort & output reports for different features | 17 | 4 |  |  | 0%
3.4 Apply validation rules in all features | 21 | 1 |  |  | 0%
3.5 User authentication | 22 | 1 |  |  | 0%
3.6 Create user comment section | 23 | 1 |  |  | 0%
3.7 Revision | 24 | 2 |  |  | 0%
3.8 Testing at the end to check out the bugs | 26 | 2 |  |  | 0%
4. Testing
4.1 Unit testing | 14 | 14 |  |  | 0%
4.2 Requirement acceptance testing | 28 | 3 |  |  | 0%
5. Closure |  |  |  |  | 0%
5.1 Deployment | 29 | 1 |  |  | 0%
5.2 Create user manual | 30 | 1 |  |  | 0%
5.3 Create data analysis report | 31 | 1 |  |  | 0%
5.4 Reports & documentation | 32 | 2 |  |  | 0%
5.5 Presentation | 34 | 1 |  |  | 0%
5.6 Lesson learned | 35 | 1 |  |  | 0%